## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 02-02-2026 | 16-02-2026 | Priyanshi Gaur | Project planning, UI wireframing, data understanding | Starting development without proper requirement analysis | Clearly defining scope and dataset structure | Created structured plan and initial architecture
2 | 2 | 17-02-2026 | 18-02-2026 | Priyanshi Gaur | Setting up frontend with proper component structure | Mixing UI logic with backend processes | Building reusable UI components | Developed base UI with modular components
3 | 3 | 19-02-2026 | 28-02-2026 | Priyanshi Gaur | Implementing secure authentication and database connections | Storing sensitive data directly in code | Following secure coding practices | Integrated authentication system securely
4 | 4 | 29-02-2026 | 10-03-2026 | Priyanshi Gaur | Building scalable recommendation system pipeline | Manual and repetitive testing of recommendations | Using automated data preprocessing techniques | Developed and tested recommendation models
5 | 5 | 11-03-2026 | 2026-04-01 | Priyanshi Gaur | Integrating backend APIs dynamically with frontend | Managing unnecessary or duplicate states | Efficient API handling and async operations | Connected recommendation engine with UI
6 | 6 | 23-03-2026 | 2026-04-02 | Priyanshi Gaur | Implementing complete cart and order workflow | Keeping unused or incorrect test data in database | Performing continuous end-to-end testing | Built cart system and simulated payment flow